## Summary
PROJECT DASHBOARD SUMMARY
Project Manager |  |  | shailendra birthare
Report Date |  |  | 2014-12-08
Project Name |  | Start Date | Planned End Date | Status | Summary of Project Status
Johnas |  | 2014-09-20 | 2015-07-20 | Yellow | The release involved new feature as well as some bug fixes.The release planning is dynamic in nature.
Green | Project is as per plan. No deviation. No Risk or Issues
Yellow | Project has slight deviation. Low priority Risk or Issues
Red | Project is deviating from plan. Needs attention. High Priority Risk or Issues

## Johnas
Johnas 1.1 Status Report for Week 1
Project Sprint/ Milestone Details | [5 empty] | Payment Details
# of Sprints/ Milestones Planned | 1 |  | Current Sprint #/ Milestone | 1 |  | Invoice Number | Invoiced Effort | Invoice Status
Sprint #/ Milestone | Start Date | End Date | Sprint Demo/Released Date | Client/UAT feedback received Date | Remarks | 4684 | 227 | Pending
[6 empty] | 4685 | 88 | Pending
Sprint1 | 2014-09-20 | 2015-07-20 |  | 2014-09-21 | Sprint released succesfully | 4732 | 275 | Pending
[6 empty] | 4733 | 96 | Pending
[6 empty] | 4781 | 337.7 | Pending
[6 empty] | 4782 | 80 | Pending
Resource & Effort Details | [5 empty] | Change Request Details
Role(As per SOW) | Resource Name |  | Available Efforts (As per SOW) | Consumed Efforts Till Date | Status | Change Request Number | Received Date | Status
Sr. S/W Developer | Pankaj Maholkar |  | 100 | 100 | Fully utilized
S/W Developer | Ganesh Todkar |  | 100 | 100 | Fully utilized
Sr. Designer | Mrugesh Phatak |  | 100 | 50 | Shared with Johnas and other projects as and when needed.
Business Analyst | Swapna Girija |  | 100 | 100 | Fully utilized
Risk/ Issue / Customer Complaints | [5 empty] | Infrastructure Details
Description |  | Status | Planned Action |  | Remarks | Development/QA | UAT | Production
No Risk Identified