## Backlog
Theme | User Story | Tasks | Business Priority | Complexity | Remarks | Sprint
Admin | As an admin, I want to login into the system so that I can access my dashboard and perform functions. | Create a login page for admin. | 13 | 5
|  | Let the user login into system with correct credentials. | 13 | 5
| As an admin, I can setup a new test with basic test details. | Create test creation page. | 21 | 13 |  | 1
|  | I can set time duration for test. | 21 | 13 |  | 1
|  | I can set passing marks for test. | 21 | 13 |  | 1
|  | Store test details into the database. | 21 | 13 |  | 1
| As an admin, I can choose an existing tag(s) for the test so that it could be used as a filter to search tests. | Develop a search engine | 13 | 13 |  | 1
|  | Develop a tag engine | 13 | 13 |  | 1
|  |  | 13 | 13 |  | 1
| As an admin, I want to setup a custom test where I can add a new question (subjective or objective) or import from question bank for multiple times. | I can add or choose a tag for a question. | 21 | 13
|  | I can select a correct answer/answers for a question. | 21 | 13
| As an admin, I can add participants (external or internal) into the system. | Fetching data from active directory | 21 | 8
|  | Assigning participants to test | 21 | 8
| As an admin, I can publish test. | Create a publish test page. | 13 | 5
|  | Change test state to Published. | 13 | 5
|  | Send notification to users for test availability. | 13 | 5 | Good to have
| As an admin, I can view all previous tests created by me and their published status. |  | 13 | 13
| As an admin, I want to edit a test so that I can change the test configurmation. |  | 13 | 8
| As an admin, I can assign/reassign test to hide/show to selected user. |  | 13 | 13
| As an admin, I want to view all the tests in a single page to analyze the existing tests. | As an admin,I can search a test based on its category or date published. | 21 | 13
| As an admin, I can add/view all questions in question bank. | As an admin, I can add a new question with dynamic tag. | 8 | 13
|  | As an admin, I can edit a question. | 8 | 13
|  | As an admin, I can search a question by tag or text. | 8 | 13
A queston will have one of the three complexity level. E.g. Beginner, Intermediate. Advance.
| As an admin, I want to view the results by participant name or by test name. |  | 21 | 13
| As an admin, I can view statistic for tests. | Display statistics for each test e.g. how many people attempted, scores, etc. | 13 | 13
|  | Create few report pages. | 13 | 13
| As a Super Admin, I want to manage tags. | Add, Delete and List |  |  |  | 1
| Add API method for CRUD operation for test. |  |  |  |  | 1
| As an admin, I can upload and view test materials. | As an admin, I can download test materials. | 13 | 21
User | As a User, I can login to my dashboard. |  | 21 | 5
| As a external User, I can fill up a form with my personal details. | Create registration page. | 13 | 5
| As a User, I can view the tests assigned to me. |  | 13 | 8
| As a User,I can attempt a test from test list. |  | 13 | 13
| As a User, I can view the result of submitted tests. |  | 8 | 8
Good To Have | As a User, I can view and download the test materials. |  | 13 | 21
| As an admin, I can disable the keyboard during the test |  | 13 | 8
Add Odata support for reporting.

## Sprint1
| Include Angular.Bootstraps into master |  | Nilesh
| Include Angular infrastructure. |  | Nilesh
API | Add API method for CRUD operation for test. |  | 24
UI | As an admin, I can setup a new test with basic test details. | Create test creation page.
I can set time duration for test.
I can set passing marks for test.
Store test details into the database.
API | As a Super Admin, I want to manage tags.
UI | As an admin, I can choose an existing tag(s) for the test so that it could be used as a filter to search tests. | Let user select an existing tag.
Fetch tags as user type.
Preload and auto complete for tag selection.

## Sprint2
As an admin, I can add/view all questions in question bank. | As an admin, I can add a new question.
As an admin, I can edit a question.
As an admin, I can search a question by tag or text.
As an admin, I can assign a tag for the question.

## TechnicalDebt
1 | Add unit test creation support
2 | Auto login (no login page) using AD.